| - CCM Meeting Minutes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INPUT FIELDS INDICATED BY YELLOW BOXES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| MEETING DETAILS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| COUNTRY (CCM) |  |  |  |  |  | Mongolia |  |  |  |  |  |  | TOTAL NUMBER OF VOTING MEMBERS PRESENT (INCLUDING ALTERNATES) |  |  |  | 17 |
| MEETING NUMBER (if applicable) |  |  |  |  |  | 92 |  |  |  |  |  |  |  |  |  |  |  |
| DATE (dd.mm.yy) |  |  |  |  |  | 30th of Mar, 2022 |  |  |  |  |  |  | TOTAL NUMBER OF NON-CCM MEMBERS / OBSERVERS PRESENT (INCLUDING CCM SECRETARIAT STAFF) |  |  |  | 8 |
| DETAILS of person who CHAIRED the meeting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| HIS / HER NAME & ORGANISATION |  |  | First name |  |  | Ganbaatar |  |  |  |  |  |  | QUORUM FOR MEETING WAS ACHIEVED (yes or no) |  |  |  | Yes |
|  |  |  | Family name |  |  | Khuyag |  |  |  |  |  |  | DURATION OF THE MEETING (in hours) |  |  |  | 03:30 |
|  |  |  | Organization |  |  | Mongolian Employer’s Federation |  |  |  |  |  |  | VENUE / LOCATION | Highland Park, Conference hall |  |  |  |
| HIS / HER ROLE ON CCM |  |  | Chair |  |  |  |  |  |  |  |  | x | MEETING TYPE (Place ‘X’ in the relevant box) |  | Regular CCM meeting |  | x |
| (Place ‘X’ in the relevant box) |  |  | Vice-Chair |  |  |  |  |  |  |  |  | x |  |  | Extraordinary meeting |  |  |
|  |  |  | CCM member |  |  |  |  |  |  |  |  |  |  |  | Committee meeting |  |  |
|  |  |  | Alternate |  |  |  |  |  |  |  |  |  | GLOBAL FUND SECRETARIAT/ LFA ATTENDANCE AT THE MEETING (Place ‘X’ in the relevant box) |  |  | LFA | x |
| HIS / HER SECTOR* (Place ‘X’ in the relevant box) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | FPM / PO |  |
| GOV | MLBL | NGO |  | EDU | PLWD |  | KAP |  | FBO |  | PS |  |  |  |  | OTHER | x |
| x | x | x |  | x | x |  | x |  | x |  | x |  |  |  |  | NONE |  |

| - legend FOR SECTOR* |  |  |  |
| --- | --- | --- | --- |
| GOV | Government | PLWD | People Living with and/or Affected by the Three Diseases |
| MLBL | Multilateral and Bilateral Development Partners in Country | KAP | People Representing ‘Key Affected Populations’ |
| NGO | Non-Governmental & Community-Based Organizations | FBO | Religious / Faith-based Organizations |
| EDU | Academic / Educational Sector | PS | Private Sector / Professional Associations / Business Coalitions |

|  |  |  | Select a suitable category for each Agenda item (Place ‘X’ in the relevant box) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Governance of the cCM, PROPOSALS & grant management related topicS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Review progress, decision points of last meeting – Summary Decisions | Review CCM annual work plans / budget | Conflict of Interest / Mitigation | CCM member renewals/appointments | Constituencies engagement | CCM Communications /consultations with in-country stakeholders | Gender issues | Proposal development | PR / SR selection / assessment / issues | Grant Consolidation | Grant Negotiations / Agreement | Oversight (PUDRs, management actions, LFA debrief, audits) | A request for continued funding / periodic review / phase II / grant consolidation / closures | TA solicitation / progress | Other |
| AGENDA SUMMARY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| AGENDA ITEM No. |  | WRITE THE TITLE OF EACH AGENDA ITEM / TOPIC BELOW |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| AGENDA ITEM #1 |  | Present the 91st CCM meeting decision implementations, issues to be discussed at the meeting | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| AGENDA ITEM #2 |  | Preliminary review of program implementation and funding completion reports | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| AGENDA ITEM #3 |  | To discuss the oversight report of the site-visit in 4 districts of UB, Tuv, Bayan-Ulgii and Khuvsgul provinces within the framework of the CCM General Oversight; Introduce feedback from the public meeting | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| AGENDA ITEM #4 |  | Obstacles to project implementation: • CCM management, • Internal audit report of the MOH; • Human resource violations reported by the GF • Introduce the measures taken | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| AGENDA ITEM #5 |  | Presentation of the situation and measures taken under the C19RM project for the COVID-19 pandemic response | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| AGENDA ITEM #6 |  | CCM activity report for 2021-2022; Introduce the work plan for 2022-2023 |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |

To add another 'Agenda Item' highlight the entire row corresponding to the last 'Agenda Item #' in the table. Right click on the mouse and click on the ‘Insert’ menu item, then select the ‘Insert Rows Below’ option. Repeat as necessary to add additional rows.

| - MINUTES OF EACH AGENDA ITEM |  |  |  |
| --- | --- | --- | --- |
| AGENDA ITEM #1 |  | Present the previous CCM meeting decision implementations, issues to be discussed at the meeting |  |
| CONFLICT OF INTEREST. (List below the names of members / alternates who must abstain from discussions and decisions) |  |  |  |
| None |  |  |  |
| WAS THERE STILL A QUORUM AFTER MEMBERS’ RECUSAL DUE TO DECLARED CONFLICTS OF INTEREST (yes or no)> |  |  | No |
| SUMMARY OF PRESENTATIONS AND ISSUES DISCUSSED/ |  |  |  |
| Kh.Ganbaatar: The meeting was chaired by CCM Chair Mr. Kh.Ganbaatar, introduced and endorsed the meeting agenda by CCM members. |  |  |  |
| B.Oyundari: Members were briefed on the decisions of the previous 91st CCM meeting Implementation of the decisions of the previous 91st CCM meeting: (Dec 3, 2022). Issues; Implementation / Suggestions. CCM site-visit report to Dornogobi and Gobisumber provinces; • Recommendations have been sent to provinces and have not yet been implemented.. - Introduction of the Community-based assessment in Mongolia under the Multi-country grant on HIV KAP/SKPA; • Submitted a proposal to get information, what is being done under the project and the scope of the second phase of the project, via online. An online meeting will be held at that time.. - Approval of the re-programming request by the PR/MoH; • “TB high level meeting” with a budget of 61.7 million MNT and “National Conference of TB Laboratory Physicians and Specialists” with a budget of 42.5 million MNT, which is planned to be organized by the TB Surveillance and research Unit of NCCD with the support of GF. It’s not possible to organize it in 2021. Therefore, the CCM proposed to organize the above-mentioned forums and national consultations virtually within the budget of 9.2 million MNT, and to spend the remaining 95.0 million MNT on the purchase of portable digital X-ray machines for TB and Covid-19 joint detection in the domestic market. And it’s approved by CCM. • The project coordinator at the time sent the request to the GF on January 18, 2022, and the GF responded on February 17, according to the relevant regulations. No action has been taken so far and a response is awaited from the GF. Portable X-ray machines were not purchased.. - Approval of the SR/NCCD's reprogramming request; • The CCM approved the postponement of activities to 2021 to 2022.. - Outcomes of program implementations on both TB and HIV; its bottleneck; • The CCM provided recommendations to the MOH on the maintenance of 8 broken X-ray machines and on the structure of TB dispensaries.. - Present and approve the Code of Ethical Conduct and establish the Ethics Committee; • An ethics committee was established accordingly. - CCM structure; • Election of the Vice-Chair of the CCM - Representative of the MOH L.Enkhsaikhan approved by CCM. • Renewal of the Oversight Committee – The new Oversight Committee was approved by CCM.. |
| CCM Chair | Kh.Ganbaatar: In addition, the CCM has received an official request to support the NACP to procure the CD-4 count machine in Mongolia. The machine has not been used for more than a year due to its damage. / Appendix 2 / |  |  |
| CCM | B.Oyundari: The CCM organized a meeting with the PLHIV with the support of the CCM member representing the PLHIV. During the meeting, the community suggested that the CD4 counts machine, had broken down at NCCD. It has been completely inactive since February 2021. This morning, we attended the GAM report meeting with the CCM Vice-Chair and a WHO representative. At the meeting, the same situation was presented. On the previous CCM meeting, the reprogramming request to procure mobile X-ray machine was approved, but there is currently no implementation. There is an avenue to centralize this funding on more concerning issue. The valuation is about 500 million MNT. At our previous meeting, the reprogrammed funding was 95 million MNT. The request was received from the NACP of NCCD. |  |  |
| CCM Vice-Chair | L.Enkhsaikhan: There are some cases that the in general blood tests, the number of lymphocytes and leukocytes is normal, but the number of immune cells counted by CD4 is very low. 1 macroliter of blood contains 1200 CD4 cells. The problem is severe when the CD4 is less than 500. Getting below 200 and 100 is a very dangerous. It is possible for a person to pass away immediately. There is a risk of brain and other organ damage. That's why people need CD4 device to take their medicine and see if it works. I want CCM members to support on this issue. |  |  |
| WHO | P.Anuzaya: The SDG and the current National HIV / AIDS Program have three main objectives in the fight against HIV / AIDS. 1. 90% of people living with HIV will know their HIV status; 2. 90% of people who know their HIV-positive status will be accessing treatment; 3. 90% of people on treatment will have suppressed viral load According to the 2021 report of Mongolia, the target of 90-90-90 percent is 44-89-97 percent. There is a need to improve screening at the national and local level. Screening validation also needs to be improved. The lack of a CD4 counter also affects the target. We see two options for addressing CD4 deficiencies. 1. From May 1, the government and the MOH will launch a nationwide screening campaign. I think the NACP NCCD and the MOH need to focus on whether funding is available. 2. The National Program on Combating and Preventing Infectious Diseases for 2016-2021 has been successfully implemented. The core program was evaluated in December last year. We are receiving information in cooperation with the MOH. We are also setting up a working group. At the last meeting of the working group, sub-program evaluation reports were discussed. In the future, the policy of the MOH is to develop an action plan. In particular, the government should gradually plan budget funding for future sustainability, including improving laboratory capacity. Medical staff should be provided with capacity building, and maintenance should be carried out in the event of a breakdown. |  |  |
| PLWD | Ts.Purevjav: At PLHIV meeting by CCM, there was an issues addressed that it is not possible to treat newly diagnosed patients because it is not possible to count the immune cells for those who got infected. As a member representing PLHIV, I want you to pay attention on this and support on today’s meeting. |  |  |
| NGO | Ch.Semjidmaa: When concluding a procurement contract, we need to consider a potential risk related to maintenance, etc. |  |  |
| CCM Chair | Kh.Ganbaatar: In principle, it was necessary to discuss additional issues. A total of 42 X-ray machines were procured nationwide, 12 of which were out of order now. Health Minister issued an order about the maintenance of X-ray machine from local fund. However, this work has been delayed. We discussed this issue with the executive committee and consulted with the stakeholders in Mongolia. I want to propose to transfer the above budget to procure CD4 count machine at NCCD. The CCM members will discuss this issue and report the desicion to the GF. |  |  |
| SUMMARY OF SPECIFIC CONTRIBUTIONS / CONCERNS / ISSUES AND RECOMMENDATIONS RAISED BY CONSTITUENCIES ON THE CCM |  |  |  |

| SUGGESTION(S) |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. When concluding a contract, pay attention to sudden risks, such as maintenance. 2. The MOH’s plan to improve laboratory capacity should be included in the plan, and the government should gradually plan budget funding to ensure sustainability. 3. Capacity building of health workers 4. Improve HIV / AIDS screening |  |  |  |  |  |  |  |  |  |  |  |  |
| DECISION(S) |  |  |  |  |  |  |  |  |  |  |  |  |
| Voting was held to purchase a CD-4 counting machine. Approved by 100% of the CCM members in Conference hall. |  |  |  |  |  |  |  |  |  |  |  |  |
| DECISION MAKING |  |  |  |  |  |  |  |  |  |  |  |  |
| MODE OF DECISION MAKING (Place ‘X’ in the relevant box) |  |  | CONSENSUS* |  |  |  | IF 'VOTING' WAS SELECTED, INDICATE METHOD AND RESULTS |  |  |  |  |  |
|  |  |  | VOTING |  | x |  | VOTING METHOD (Place ‘X’ in the relevant box) |  | SHOW OF HANDS |  |  | x |
|  |  |  |  |  |  |  |  |  | SECRET BALLOT |  |  |  |
|  |  |  |  |  |  |  | ENTER THE NUMBER OF MEMBERS IN FAVOUR OF THE DECISION> |  |  |  |  | 17 |
|  |  |  |  |  |  |  | ENTER THE NUMBER OF MEMBERS AGAINST THE DECISION> |  |  |  |  |  |
| *Consensusisgeneral or widespread agreement by all members of a group. |  |  |  |  |  |  | ENTER THE NUMBER OF VOTING CCM MEMBERS WHO ABSTAINED> |  |  |  |  |  |
| AGENDA ITEM #2 |  | Preliminary review of program implementation and funding completion reports |  |  |  |  |  |  |  |  |  |  |
| CONFLICT OF INTEREST. (List below the names of members / alternates who must abstain from discussions and decisions) |  |  |  |  |  |  |  |  |  |  |  |  |
| None |  |  |  |  |  |  |  |  |  |  |  |  |
| WAS THERE STILL A QUORUM AFTER MEMBERS’ RECUSAL DUE TO DECLARED CONFLICTS OF INTEREST (yes or no)> |  |  |  |  |  |  |  |  |  |  |  | No |
| SUMMARY OF PRESENTATIONS AND ISSUES DISCUSSED |  |  |  |  |  |  |  |  |  |  |  |  |
| Introduce the implementation of the project in 2021 with the assistance of the MOH and the Global Fund S.Ganzaya, Senior Research Specialist of the Global Fund-supported AIDS and TB Project / Appendix 3 / |  |  |  |  |  |  |  |  |  |  |  |  |
| Brief introduction 2021.01.01-2022-2023.12.31 TB 10,718,269 USD HIV/AIDS 2,626,061 USD COVID-19 4,837,763 USD Total: $ 18,182,093 Purpose: Provide comprehensive human-centered TB services, introduce innovative methods of case detection and diagnosis, expand multilateral cooperation, and reduce the spread of HIV and AIDS-related deaths. Objective: • Increase TB treatment coverage to 55% by 2023 • Maintain TB treatment success above 90 percent • Provide comprehensive patient-centered health care by expanding multilateral cooperation • Increase the detection of HIV infection • Intensify HIV prevention and keep the disease low in high-risk populations. • Strengthen cooperation and coordination between government and non-government organizations 2021-2022 financing and its expenditure status Module; Approved budget 2021; Expenditure; Balance. 1; Drug-resistant TB care; 715,893.85; 40%; 426,652.18. 2; Health information system management and monitoring and evaluation; 224,748.00; 24%; 170,635.14. 3; TB care and prevention; 2,364,030.67; 41%; 1,405,954.57. 4; Provide comprehensive care and improve quality; 509,300.62; 65%; 178,413.13. 5; Community systems strengthening; 240,574.70; 89%; 26,502.67. 6; TB/HIV; 18,062.00; 36%; 11,522.31. 7; Laboratory system; 505,884.78; 14%; 433,590.52. 8; Program management; 433,723.50; 87%; 57,725.08. 9; Human resources and volunteers; 102,583.90; 77%; 23,520.71. 10; HIV differential diagnosis and testing; 78,846.50; 64%; 28,071.20. 11; Prevention; 184,106.10; 87%; 23,958.92. 12; Reduce human rights barriers to HIV / TB services; 46,955.00; 35%; 30,429.68. 13; Financial management system; 9,000.00; 11%; 8,042.19. 14; Health sector management and planning; -; -; -. 15; Treatment, care and support; 12,000.00; 96%; 508.96. 20; Covid-19; 3,432,415.92; 42%; 1,999,983.82. Total; 8,878,125.55; 46%; 4,825,511.09. Funding and expenditures for 2021-2022 by SR each SRs; Approved budget 2021; Expenditure; Balance. 1; MOH; 2,674,012.09; 38%; 1,666,401.31. 2; Surveillance and research Unit of NCCD; 2,726,082.62; 26%; 2,013,926.11. 3; Mongolian Association of Soum Doctors; 394,921.10; 83%; 65,520.36. 4; Mongolian Anti-Tuberculosis Association; 860,318.15; 62%; 325,990.29. 5; Mongolian Red Cross Society; 170,050.00; 94%; 10,747.55. 6; Mongolian Association of Family Medicine Specialists; 705,430.73; 54%; 323,765.20. 7; Prison-429; 158,163.36; 32%; 106,945.50. 8; TB free future; 136,427.00; 89%; 14,525.17. 9; TB department, NCCD; 251,055.12; 42%; 145,605.32. 10; “Healthy Future Without TB” NGO; 536,154.47; 83%; 90,334.87. 11; Perfect Ladies NGO; 265,510.92; 77%; 61,749.42. amount; 8,878,125.55; 46%; 4,825,511.09. Project criteria: As of the end of 2021 Indicator; Objective; Fulfillment; Performance. 1; TB I-3 (M): TB mortality rate, 100,000 population; 7.3; 5.5. 2; TB I-4 (M): Prevalence of rifamycin (RR-TB) and / or MDR-TB among new TB cases; 7%; 5.3%. 3; TB O-4 (M): Success in treatment with rifamycin resistance and MDR-TB; 60%; 72.3%; 120%. 4; TB O-5 (M): TB treatment coverage; 45%; 20.8%; 46%. 5; TCP-1 (M): Number of all registered TB cases; 6,581; 2709; 41%. 6; TCP-2 (M): Success in the treatment of all forms of TB; 91%; 90%; 99%. 7; TCP-5.1: Number of people receiving TB treatment for contact prevention; 1350; 201; 15%. 8; TCP-6a: Cases of TB (all forms) reported among prisoners; 76; 56; 74%. Indicator; Objective; Fulfillment; Performance. 9; MDR TB-2 (M): Number of reported cases of rifamycin-resistant and MDR-TB; 355; 131; 37%. 10; MDR TB-3 (M): Rifampicin-resistant and MDR-TB incidence in second-line drug treatment of TB; 355; 120; 34%. 11; MDR TB-6 (M): Percentage of TB patients screened for rifampicin at an early age; 75%; 89.7; 120%. 12; 12 MDR TB-7.1 (M): Rifampicin-resistant and MDR-TB incidence in 2nd line TB health testing; 70%; 78.2; 112%. 13; TB / HIV-6 (M): Number and percentage of HIV / TB patients receiving antiretroviral therapy during TB treatment; 100%; 100%; 100%. Indicator; Objective; Fulfillment; Performance. 14; KP-1a - Percentage of men having sex with men living with HIV prevention program; 3925; 3897; 99%. 15; KP-1c (M): Percentage of sex workers enrolled in HIV prevention programs; 3213; 3327; 101%. 16; HTS-3a (M): Percentage of men who have sex with men who have been tested for HIV and know the results; 3532; 3231; 91%. 17; HTS-3c (M): Percentage of sex workers who have been tested for HIV and know the results; 3031; 3225; 106%. 18; TCS-1.1 (M): Percentage of patients living with HIV receiving ART; 369; 238; 64%. Sample transportation from soum to province Year; Percentage of samples transported Soum; Number per person; Number of samples transported per person; Positive detection. 2019 он; 90%; 7361; 14722; 501. 2020 он; 93.5%; 6360; 12695; 402. 2021 он; 80%; 4292; 8583; 523. |
| SUMMARY OF PRESENTATIONS AND ISSUES DISCUSSED. WHO; P.Anuzaya: According to the budget expenditure category, it is 87 percent on the 11th preventive expenditure. On top of that, 13 percent is left after deducting the cost of the investment. Was it spent on HIV/AIDS prevention activities or on TB prevention? About drug balance and warranty period? Focus on your next plan and prevention.. PCU; G.Ganzaya: The 8.8 million allocated in the cost category has been provided for 3 activities such as AIDS, TB and Covid-19. Although 184,000 USD was purchased for the supply of drugs needed to prevent close contact with TB patients, Criterion 7 was not good enough due to insufficient TB screening. The warranty period for TB drugs is 2-2.5 years. Because isoniazid is a pill, there is no risk of expiration.. PLWD; Ts.Purevjav: Are you doing preventive treatment for TB and HIV? I think that the performance of people living with HIV will be higher if we exclude people living abroad and those who have passed away.. PCU; G.Ganzaya: In 2021, we are conducting preventive treatment without any age limit. HIV prophylaxis is very rare and has been talked about for a long time. B.Gansukh: In 2021, according to the estimation, there were more than 620 people living with HIV. Of those, 369 were targeted for antiretroviral treatment. 238 people are receiving antiretroviral treatment and the number of people who have stopped treatment and those who are abroad is not being counted according to the criteria definition.. NGO; Ch.Semjidmaa: Do you do preventive work in connection with alcohol addiction? What has been done to protect the human rights of people with TB?. PCU; G.Ganzaya: There is a center for involuntary treatment of alcohol and drug users. People in Prison No. 429 are undergoing our preventive screening. However, issues related to alcoholism and homelessness are being investigated by the Mongolian Red Cross Society. B.Gansukh: The HIV / AIDS and TB project is being implemented in an integrated manner, which is different from previous projects. Expenditures appear to be higher due to the consolidation of total budgets for STI activities at risk group people.. KAP; B.Bayarmaa: In terms of procurement, SRs has not yet received IT equipments such as printers and computers, when will this be resolved?. PCU; D.Bat-Oyun: The purchase of SR office equipment was carried out in 2021 in accordance with the law on procurement of goods and services with local funds. Following the procurement under this law, the allocation was by the Health Minister’s order. In response, the NGO said that it was not possible to distribute to the organizations, so the allocation was made to the PCU, and the contract was prepared and sent to the SR companies for use. All SR agreements have been signed and will be approved by the MOH and handed over to SR.. FBO; J.Odgarid: One of the issues I noticed during the site-visit was that the sputum transportation was not going well. So how do you get such high rating?. PCU; G.Ganzaya: Out of 331 soums, the number of soums transported sputum is calculated as a percentage. As of 2021, 68 soums did not carry sputum at all. In 2021, the sputum transportation process was interrupted=. In the past, we used to pay for the transportation to soum hospitals through the health department. It was given to the soum doctors' association, and from there it was given to the province health department under three contracts, and from there the soum collected the documents and received the funding. There are many difficulties in recovering these funds from government accounts. From 2022, it is believed that giving incentives to a person who transports the sample will have a greater impact on quality.. FBO; J.Odgarid: It seems that the SRs are causing an additional burden in the process. In the past, the district and provinces went to health department and distributed from there, which may have helped to cooperate with the general hospital and dispensary.. PCU; G.Ganzaya: We tried to implement the project through government organizations. In 2018, it was withdrawn from NGOs to be given directly to the province's general hospital and health department. However, we did not receive any reports from government organizations. According to the report, the target group was not reached. Therefore, SR is conducted by organizations involved in capacity assessment that meet the requirements of the GF.. CCM Chair; Kh.Ganbaatar: Our members have been very active and supportive in their site-visits. Ensure that SR is carried out in a quality and efficient manner. Many of these organizations need to be improved. Make a specific request of sputum transportation to MOH. Submit a formal request to the MOH to increase staff in Darkhan-Uul province, Songikhairkhan district, Chingeltei district, Bayanzurkh district. Submit a proposal to the General Department of Health Insurance and Health Minister to include STI / AIDS and TB specifically in the health screening starting on May 1. Involve alcoholics in screening. Together with CCM members and Ganzaya, we will present our issues to the Health Minister. During the online meeting with the GFs, we will discuss how to intensify the implementation of the provisions that have been suspended in Mongolia, and if necessary, we will write a letter to the Health Minister.. CCM Vice-Chair; L.Enkhsaikhan: In the screening that will start in May, the Health Minister has talked about coordinating the activities of the GF. Have someone deliver drugs to soums. In terms of antenatal care, 1 in 3 people did not have antenatal care. People were also not good enough to see a conscious doctor. STI and TB screening is really inadequate. The e-conference organized by R&D was really irresponsible. People who use drugs or alcohol are excluded from STI testing. We need to pay attention to this. It is said that a lot of TB tests have been done, but the quality is also poor.. GOV; I.Baatarkhuu: We need to ensure good coordination between organizations. This is not just a matter for the health care system or the MOH’s task, and it will not work if we focus on it alone. The involvement of organizations such as cross-sectoral or welfare labor should be ensured. Family Medical Center and Health Centers need to work together on areas where people are not covered. The Department of City Governor`s Office believes that there is nothing wrong with mobilizing all efforts such as the Ulaanbaatar Health Department, district health centers, and khoroos to prevent TB / AIDS screening in Ulaanbaatar.. |
| 2 SUMMARY OF SPECIFIC CONTRIBUTIONS / CONCERNS / ISSUES AND RECOMMENDATIONS RAISED BY CONSTITUENCIES ON THE CCM |  |  |  |  |  |  |  |  |  |  |  |  |
| DECISION(S) |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Ensure that SR is carried out in a quality and efficient manner. 2. Submit a formal request to the MOH to increase the capacity of human resource in Darkhan-Uul province, Songikhairkhan district, Chingeltei district, Bayanzurkh district 3. Submit a proposal to the Health Minister to include STI / AIDS and TB specifically in the health examination starting on May 1. 4. Involve alcoholics in screening. Introduce the issue to the Health Minister with CCM members and Ganzaya, PCU 5. During the online meeting with the GFs, the implementation of the provisions that have been suspended in Mongolia will be discussed and, if necessary, a letter will be sent to the Health Minister. |  |  |  |  |  |  |  |  |  |  |  |  |
| DECISION MAKING |  |  |  |  |  |  |  |  |  |  |  |  |
| MODE OF DECISION MAKING (Place ‘X’ in the relevant box) |  |  |  | CONSENSUS |  | * |  | IF 'VOTING' WAS SELECTED, INDICATE METHOD AND RESULTS |  |  |  |  |
|  |  |  |  | VOTING |  |  |  | VOTING METHOD (Place ‘X’ in the relevant box) |  | SHOW OF HANDS |  |  |
|  |  |  |  |  |  |  |  |  |  | VOTE |  |  |
|  |  |  |  |  |  |  |  | ENTER THE NUMBER OF MEMBERS IN FAVOUR OF THE DECISION > |  |  |  |  |
|  |  |  |  |  |  |  |  | ENTER THE NUMBER OF MEMBERS AGAINST THE DECISION > |  |  |  |  |
| *Consensusisgeneral or widespread agreement by all members of a group. |  |  |  |  |  |  |  | ENTER THE NUMBER OF VOTING CCM MEMBERS WHO ABSTAINED> |  |  |  |  |
| AGENDA ITEM #3; To discuss the oversight report of the site-visit in 4 districts of UB, Tuv, Bayan-Ulgii and Khuvsgul provinces within the framework of the CCM General Oversight; Introduce feedback from the public meeting. CONFLICT OF INTEREST. (List below the names of members / alternates who must abstain from discussions and decisions). None. WAS THERE STILL A QUORUM AFTER MEMBERS’ RECUSAL DUE TO DECLARED CONFLICTS OF INTEREST (yes or no)>; No. SUMMARY OF PRESENTATIONS AND ISSUES DISCUSSED. Brief summary of the results of the general inspection of the program implementation in 4 districts of Ulaanbaatar, Tuv, Bayan-Ulgii and Khuvsgul provinces B.Nyamdulam, Oversight Specialist of the CCM Secretariat introduced. / Appendix 4 / Brief introduction • Baganuur district (Issues to be considered) TB: 2.2 points - Average Insurance and maintenance costs have not been budgeted or resolved. The number of screening is good, but the quality is insufficient Discrimination against people with TB AIDS: 2 points - Average Bad for customers Pregnancy STIs increased • Nalaikh district (Issues to be considered) TB: 2.2 points - Average Insurance and maintenance costs have not been budgeted or resolved Mechanized ventilation system does not work Insufficient coverage of latent TB infection treatment. AIDS: 2 points - Average There is no specialist. GF-funded trained human resources were eliminated • Chingeltei district (Issues to be considered) TB: 2 points - Average Infection prevention facilities operate in substandard facilities Lack of human resources There is a lack of support from other sectors to improve the monitoring of TB patients AIDS: 1.8 points - Needs improvement Jobs that are not tailored to the specifics of the activity are not provided • Songinokhairkhan district (Issues to be considered) TB: 2 points - Average Insufficient use of portable X-ray machines Remote care Homeless and homeless people have difficulty monitoring TB treatment AIDS: 1.8 points - Needs improvement Unscrupulous environment Pregnancy control is difficult • Issues related to health insurance Uninsured and at-risk individuals find it difficult to access medical care. Cooperation proposal presented by the CCM among the decision makers from the UB City Mayor office and district governors meeting: Tuberculosis: • Insure high-cost equipment and plan for recurrent costs • Co-organize detection across sectors • Support the improvement of treatment quality control • Expand information, training and advocacy STIs, HIV, AIDS: • Increase human resources • Provide tailored workplaces • Improving diagnostic capabilities • Insurance • Zaamar soum of Tuv province (Issues to be considered) TB, AIDS, STIs: 3 points Temporary residents, even stateless residents Performance financing • Bayan-Ulgii province (Issues to be considered) TB: 2.5 points - Average High-cost equipment supplied by GI, such as Portable X-rays and Gen-Expert, are covered. AIDS: 1 point - Needs improvement • Unfair to customers. It is mixed with antenatal care. • No detection or diagnosis. • Khuvsgul province (Issues to be considered) TB: 2.5 points - Average The portable X-ray is broken AIDS: 2 points - Average Unfavorable environment for clients and medical staff Lack of human resource Cannot get full funding from insurance Questionnaire survey among the KAP beneficiaries of the Global Fund project N = 13 -Reaching more people, sharing information on social media in the age of internet, presenting your project to the public in a more creative way Survey of PLWD/HIV benefiting from the Global Fund project N = 13 -Continue food and financial support. MOH; J.Narangerel: In the survey, did the questionnaire from 13 people really represent the whole community?. PLWD; Ts.Purevjav: The survey was conducted by gathering people living with HIV. There are about 230 PLWD/HIV in Mongolia. There are hardly any people who would reveal their identity. So those people have the ability to represent. And they able to bring up the problem exactly.. NGO; B.Tuya: The information flow to the public is insufficient. The general population needs to be informed about HIV. Small press conferences and information can be provided. For example, information can be released to the public on December 1. Employ trained doctors, such as health centers and district hospitals, and build the capacity of those doctors. Training should be provided, such as protecting personal privacy. Our organization can cooperate in this regard.. NGO; Ch.Semjidmaa: Projects and programs are inconsistent in terms of training doctors. For example,there are some activity overlaps with other entities, therefore, to coordinate with other organizations such as the World Bankin this regard... GOV; I.Baatarkhuu: It has been 32 years since the transition from a centrally planned economy to a market economy. During this time, huge projects and programs have been implemented in all sectors. In times when a project or program stops, all activities stop immediately. Sustainability is poor in our context. The government needs to improve coordination, and the The Department of City Governor’s Office only registers. There are numerous ongoing project, and we cannot influence the decision to ensure sustainability.. KAP; B.Bilguun: Transgender people are most vulnerable to any discrimination and violence. Due to the fact that transgender girls work at nighst, they are more likely to rest during day time when health care service is held. There is a need for medical services to work in extensive hours such as in the evenings.. PLWD; Ts.Purevjav: Implementation is insufficient due to lack of funding at the soum and district levels. I wonder where the GF money goes? Why are there so few STI and TB doctors? Is the salary low, the job boring, or is it so overwhelming?. PCU; G.Ganzaya: We provide support to soum and primary health care facilities, such as the cost of transporting sputum and the cost of examining patients with TB. In terms of funding, 2021 is a quarter behind. This year is also one month late. Wages are very low compared to the workload.. PCU; B.Gansukh: Students are interested in working in a private clinic. Those who choose a profession should be well supported from the beginning.. FBO; J.Odgarid: More attention is needed on STIs. Due to lack of human resource, the old work was regressed by several stages. I want the CCM to pay attention to this. Are there any plans to increase screening or human resource? The CCM Secretariat has conducted a survey from PLWD/HIV. Is there any survey in the PCU?. PCU; B.Gansukh: During the project development, we try to look through the big window as much as possible. Two years ago, when I saw a problem with human resources, 60 doctors were trained in three years. In the case of the AIDS project, all funding is provided to the affected population, and there are no activities aimed at the entire population. MSM focuses on transgender people. In collaboration with the National Center for Human Resource Development and the MOH, we worked to turn a 6-year graduate of the Academy of Sciences into a 1-year STI doctor. There are small studies on the project. A survey of 6,500 sex workers was conducted in Mongolia. The study also estimated that there are about 6,000 MSM.. WHO; P.Anuzaya: I think we should pay attention to the measures to be taken. Provide suggestions on how to improve care in terms of the program. Advise on how to improve primary care and how to integrate primary and secondary care. 2. We are working on systematizing the transportation of sputum or proposing how to get funding from the state budget and make it a policy in the future. Sampling should be evaluated. 3. Sustainability or health care needs to be established. This requires proper medium and long-term planning. I think the policy level needs to be stable, such as whether it can be reflected in the law.. CCM Chair; Kh.Ganbaatar: We need to focus on transition and sustainability plan. Once the recommendations of the seven units have been received, they should be consolidated and submitted to the MOH. We will talk about this during our meeting with the MOH. HIV/AIDS, TB activities of the GF should be addressed in the Law on Public Health Services .. ANSWER(S) Summarize the answer in the section below. Focus on transition and sustainability. DECISION(S) Summarize the decision in the section below. 1. Consolidate the recommendations of the seven units and submit a proposal to the MOH 2. Include GF’s HIV / AIDS and TB activity in the Public Health Care Law. DECISION MAKING. MODE OF DECISION MAKING (Place ‘X’ in the relevant box); CONSENSUS; *; IF 'VOTING' WAS SELECTED, INDICATE METHOD AND RESULTS. VOTING; VOTING METHOD (Place ‘X’ in the relevant box); SHOW OF HANDS. VOTE. ENTER THE NUMBER OF MEMBERS IN FAVOUR OF THE DECISION >. ENTER THE NUMBER OF MEMBERS AGAINST THE DECISION >. *Consensusisgeneral or widespread agreement by all members of a group.; ENTER THE NUMBER OF VOTING CCM MEMBERS WHO ABSTAINED>. AGENDA ITEM #4; Obstacles to project implementation. CONFLICT OF INTEREST. (List below the names of members / alternates who must abstain from discussions and decisions). None. WAS THERE STILL A QUORUM AFTER MEMBERS’ RECUSAL DUE TO DECLARED CONFLICTS OF INTEREST (yes or no)>; No. SUMMARY OF PRESENTATIONS AND ISSUES DISCUSSED. Implementation of the project in 2021 with the support of the MOH and the Global Fund S.Ganzaya, Senior Research Specialist of the Global Fund-supported AIDS and TB Project introduced / Appendices 5,6,7 / According to the “Internal Audit Plan 2021” approved by the Portfolio Minister of Health Date of assessment: October 2021, Department of Monitoring, Evaluation and Internal Audit of the MOH Year of enrollment: 2020 Object: MNG-H-MOH-1460; MNG-T-MOH-1465 Evaluated by: S.Tugsdelger, Head of Internal Audit Unit, T.Bolorchimeg, Head, D.Tungalag Scope: Global Fund-funded AIDS / TB project activities Date of submission of the report: December 27, 2021, official number 8/6945 The report has a total of 15 pages, and one appendix. Purpose • Internal audit of the Global Fund-funded AIDS / TB project activities, plans, objectives, financial operations, transparency, glass accounts, and cooperation with project implementing agencies. • To support the unit's activities by evaluating the issues, preventing risks, eliminating identified deficiencies, and developing recommendations to improve operations. To ensure the implementation of the recommendations: • Update internal regulations- 8 • Update Command-3 • Contract evaluation-1 • Concluding a contract-1 • Repayment of assets - 12.5 million MNT • Unknown-7. CCM Chair; Kh.Ganbaatar: If these issues are not addressed, projects in Mongolia will be in high risk. We are concerned that the support is not interrupted in any way. You need to provide an answer based on legal grounds.. FBO; J.Odgarid: It is unethical to send any complain directly to the GF without prior undergoing through the CCM without the supervision of the MOH. The PCU, has lost its order in resolving internal issues. We need to pay attention to this in the future. We should not have a conflict of interest, but SR is a member of this CCM. There is chaos. Members are expressing their support for the project in Mongolia. A working group should be set up to make recommendations accordingly. There is an individual tendency to overcome problems. We want to resolve issues related to members with potential conflicts of interest and PCUs internal issue.. CCM Vice-Chair; L.Enkhsaikhan: The GF's head office’s, which has been respectfully supporting our country, faith in us is fading. Help must be given to those who need it. It is unfortunate that the PCU send iformation directly to the GF without reporting to the MOH and CCM.. CCM Chair; Kh.Ganbaatar: GF people aren’t that disappointed in Mongolia. But, The situation needs to be corrected immediately. The answer should be signed by the Minister of Health. If left unchecked, this could put the project at risk. A member with a conflict of interest should be released. We would like to inform you that the CCM has decided to improve its work with the MOH and the PCU in accordance with its previous responsibilities. The CCM will support the CCM to correct its mistakes. It is proposed to set up a working group on this. We need to stop dealing directly with GF without our knowledge. Let's not stop the project, let's work together to continue.. FBO; J.Odgarid: Let's set up a working group to support and cooperate on this issue.. ANSWER(S). DECISION(S). A working group was set up to work on the PCU 1. J.Odgard, Head of the Working Group, Representative of a religious organization 2. B.Tuya, Representative of HIV NGO 3. Ch. Samjidmaa, Representative of a human rights NGO 4. L.Bayartsetseg, Member of the Oversight Committee, 5. Ts. Purevjav, PLWD/HIV. DECISION MAKING. MODE OF DECISION MAKING (Place ‘X’ in the relevant box); CONSENSUS; *; IF 'VOTING' WAS SELECTED, INDICATE METHOD AND RESULTS. VOTING; VOTING METHOD (Place ‘X’ in the relevant box); SHOW OF HANDS. VOTE. ENTER THE NUMBER OF MEMBERS IN FAVOUR OF THE DECISION >. ENTER THE NUMBER OF MEMBERS AGAINST THE DECISION >. *Consensusisgeneral or widespread agreement by all members of a group.; ENTER THE NUMBER OF VOTING CCM MEMBERS WHO ABSTAINED>. AGENDA ITEM #5; Presentation of the situation and measures taken under the C19RM project for the COVID-19 pandemic response. CONFLICT OF INTEREST. (List below the names of members / alternates who must abstain from discussions and decisions). None. WAS THERE STILL A QUORUM AFTER MEMBERS’ RECUSAL DUE TO DECLARED CONFLICTS OF INTEREST (yes or no)>; No. SUMMARY OF PRESENTATIONS AND ISSUES DISCUSSED. IMPLEMENTATION OF SUPPLEMENTARY PROJECTS TO PREPARE COVID-19 RESPONSE MEASURES /2021.07.01 - 2022.03.30 / G.Gantungalag, C19RM Project Specialist / Appendix 8 / Overview: NCCD AIDS / STI Surveillance Research Unit: ($ 215,669) • Introduced an interactive learning platform. • A psychologist is working to provide psychological counseling and support to people living with HIV. • Introduced Call Pro service for patients with HIV and STIs • Electronic monitoring of HIV-infected patients • Mobile care for HIV-infected patients / home delivery of drugs and regular testing / Youth Health Center NGO: ($ 302,862) • The distribution of food and vitamin packages to the at-risk population under the supplementary project was a more effective support and had a positive impact on the implementation of the project criteria. • The development and implementation of e-learning courses and online information platforms is effective in providing information to the undercover community. • The provision of food and vitamin packages to people living with HIV has enabled the community to volunteer for monthly monitoring and treatment. • The training of psychologists and the provision of free counseling to those in need have become a popular service. Perfect Women NGO: ($ 76,787) • Prepared a comprehensive video course on 13 STI, HIV and AIDS distance learning topics for female sex workers and outreach and case managers. • Food aid packages for female sex workers were distributed to 1,200 sex workers. The food aid package has been effective in supporting the livelihoods of sex workers who have lost their jobs during the quarantine period, when bars, karaoke, hotels and saunas were closed. • Additional funding activities have had a significant impact on the achievement of the criteria for quality and provision of HIV and STI services for sex workers. Support the implementation of the COVID-19 pandemic response plan Activity: MOH ($ 2,129,940) • The process of issuing an order from the Minister of Health on the distribution of equipment, medicines and medical supplies has been too slow. The ordered supplies and medical supplies were not delivered to the units on time. • Increased transportation costs and delayed transportation. • The procurement items included in the project are not based on a “needs assessment”. • Due to time constraints in e-learning, application development, and website and platform development, it was difficult to launch on time. • Food prices and purchases of vitamins have been affected by the increase in prices due to quarantine and closed borders during the pandemic.. NGO; B.Tuya: Is it possible to give us an interactive program? And handbook. Monitoring should be done well. If there are errors at that time, there should be monitoring to correct them.. PLWD; Ts.Purevjav: Are you presenting the report directly from SR?. CCM; G.Gantungalag: The report received directly from the PCU did not reveal any problems, so a qualitative study was conducted. Monitored during project implementation. We met and supported the PCU and SR.. WHO; P. Anuzaya: We need to evaluate the economic efficiency and analyze the impact.. CCM Chair; Kh.Ganbaatar: If there are any shortcomings, we should pay attention to correcting them.. ANSWER(S) Summarize the answer in the section below. DECISION(S) Summarize the decisio. 1. Assess economic efficiency and analyze the impact in the section below 2. Provide the CCM with an interactive program and guidebook 3. If there are any shortcomings, care should be taken to correct them.. DECISION MAKING. MODE OF DECISION MAKING (Place ‘X’ in the relevant box); CONSENSUS; *; IF 'VOTING' WAS SELECTED, INDICATE METHOD AND RESULTS. VOTING; VOTING METHOD (Place ‘X’ in the relevant box); SHOW OF HANDS. VOTE. ENTER THE NUMBER OF MEMBERS IN FAVOUR OF THE DECISION >. ENTER THE NUMBER OF MEMBERS AGAINST THE DECISION >. *Consensusisgeneral or widespread agreement by all members of a group.; ENTER THE NUMBER OF VOTING CCM MEMBERS WHO ABSTAINED>. AGENDA ITEM #6; CCM activity report for 2021-2022; Introduce the work plan for 2022-2023. CONFLICT OF INTEREST. (List below the names of members / alternates who must abstain from discussions and decisions). None. WAS THERE STILL A QUORUM AFTER MEMBERS’ RECUSAL DUE TO DECLARED CONFLICTS OF INTEREST (yes or no)>; No. SUMMARY OF PRESENTATIONS AND ISSUES DISCUSSED. CCM Activity Report 2021-2022 B.Oyundari, Coordinator of the CCM Secretariat, introduced. / Appendices 9, 10, 11, 12 / Overview: • Funding - 60,000 • Additional funding for the C19RM project — 15,000 • Position of the CCM-34,000 • TOTAL 108,900 • Exchange rate = 2850 MNT / 309,676,750 Offer with remaining funding • Equipment to improve the capacity of the CCM Secretariat; furniture • Half the cost of hosting a TB summit №; Name; Where to buy; Model; Price/Tugrugs; Number; Price. 1; Processor; BSB; Acer-N50-620-117-GTX1650, i7 RAM-8GB Hard-1 TB HDD,+256 GB SSD; 4,299,900.00; 1.00; 4,299,900.00. 2; Speaker; BSB; Soni-Titan-2; 43,900.00; 3.00; 131,700.00. 3; Mouse (wired); BSB; Dell-MS116; 29,900.00; 2.00; 59,800.00. 4; Flash; BSB; 64 HB ADATA; 59,900.00; 3.00; 179,700.00. 5; Computer Monitor; BSB; Dell-P2422H 24 inch; 849,900.00; 2.00; 1,699,800.00. 6; Fridge; BSB; 93L Single door fridge; 399,900.00; 1.00; 399,900.00. 7; Coffee Maker; BSB; BTC Coffe maker 1450W Silv; 2,099,900.00; 1.00; 2,099,900.00. 8; Microwave; BSB; Microwave oven 25L 800W; 389,900.00; 1.00; 389,900.00. 9; Web Camera; Best Computers; Grandstream GUV3100 1080P FHD USB Webcam; 181,500.00; 3.00; 544,500.00. 10; Keyboard (wireless); BSB; Logitech Wireless Keyboard K270; 104,900.00; 3.00; 314,700.00. 11; Bean Bag; Бөмбүүлэй Bean bag; 150 cm; 300,000.00; 2.00; 600,000.00. 12; Voice Recorder; BSB; ICD-PX240; 149,900.00; 1.00; 149,900.00. 13; TV; PC Mall; Samsung 75 inch TV; 3,999,999.00; 1.00; 3,999,999.00. 14; Shelf; BSB; 156x42x89; 1,403,910.00; 1.00; 1,403,910.00. 15; Glass board; MaxGlass; 2mx1; 440,000.00; 1.00; 440,000.00. Total; 16,713,609.00.. CCM; B.Oyundari: The performance evaluation form of the CCM Secretariat assessed by the CCM, therefore the performance indicators are shown on the slide as it is on the sheet. As it is performance-based funding, please fill it out and help the CCM Secretariat improve in terms of the execution.. CCM Chair; Kh.Ganbaatar: To research the purchase of tablets for CCM members. FBO; J.Odgarid: I approve to purchase CCM Secretariat office supplies.. NGO; B.Tuya: Please take care of the membership issue. Remove the expired member and elect the next CCM member.. ANSWER(S). DECISION(S). 1. Approved funding for 2022-2023. 2. The remaining funding was used to purchase furniture and equipment for the CCM office.. DECISION MAKING. MODE OF DECISION MAKING (Place ‘X’ in the relevant box); CONSENSUS; *; IF 'VOTING' WAS SELECTED, INDICATE METHOD AND RESULTS. VOTING; VOTING METHOD (Place ‘X’ in the relevant box); SHOW OF HANDS. VOTE; x. ENTER THE NUMBER OF MEMBERS IN FAVOUR OF THE DECISION >; 13. ENTER THE NUMBER OF MEMBERS AGAINST THE DECISION >. *Consensusisgeneral or widespread agreement by all members of a group.; ENTER THE NUMBER OF VOTING CCM MEMBERS WHO ABSTAINED>. |
| SUMMARY OF DECISIONS & ACTION POINTS |  |  |  |  |  |  |  |  |  |  |  |  |
| AGENDA ITEM NUMBER | WRITE IN DETAIL THE DECISIONS & ACTION POINTS BELOW |  |  |  |  |  |  |  |  |  | KEY PERSON RESPONSIBLE | DUE DATE |
| AGENDA ITEM #1 | Present the 91st CCM meeting decision implementations, issues to be discussed at the meeting 1. When concluding a contract, pay attention to sudden risks, such as maintenance. 2. The MOH’s plan to improve laboratory capacity should be included in the plan, and the government should gradually plan budget funding to ensure sustainability. 3. Capacity building of health workers 4. Improve HIV / AIDS screening Voting was held to purchase a CD-4 counting machine. Approved by 100% of the CCM members in Conference hall. |  |  |  |  |  |  |  |  |  | CCM Secretariat, NCCD | - |
| AGENDA ITEM #2 | Preliminary review of program implementation and funding completion reports 1. Ensure that SR is carried out in a quality and efficient manner. 2. Submit a formal request to the MOH to increase the number of doctors in Darkhan-Uul province, Songikhairkhan district, Chingeltei district, Bayanzurkh district 3. Submit a proposal to the Health Minister to include HIV/AIDS and TB specifically in the health examination starting on May 1. 4. Involve alcoholics in screening. Introduce the issue to the Health Minister with CCM members and Ganzaya 5. During the online meeting with the GFs, the implementation of the provisions that have been suspended in Mongolia will be discussed and, if necessary, a letter will be sent to the Health Minister. |  |  |  |  |  |  |  |  |  | PCU | - |
| AGENDA ITEM #3 | To discuss the oversight report of the site-visit in 4 districts of UB, Tuv, Bayan-Ulgii and Khuvsgul provinces within the framework of the CCM General Oversight; Introduce feedback from the public meeting 1. Consolidate the recommendations of the seven units and submit a proposal to the MOH 2. Include GF’s HIV / AIDS and TB activity in the Public Health Care Law |  |  |  |  |  |  |  |  |  | CCM Secretariat | - |
| AGENDA ITEM #4 | Obstacles to project implementation A working group was set up to work on the PCU 1. J.Odgard, Head of the Working Group, Representative of a religious organization 2. B.Tuya, Representative of HIV NGO 3. Ch.Semjidmaa, Representative of a human rights NGO 4. L.Bayartsetseg, Member of the Oversight Committee 5. Ts.Purevjav, PLWD/HIV |  |  |  |  |  |  |  |  |  | CCM members | - |
| AGENDA ITEM #5 | Presentation of the situation and measures taken under the C19RM project for the COVID-19 pandemic response 1. Assess economic efficiency and analyze the impact 2. Provide the CCM with an interactive program and guidebook 3. If there are any shortcomings, care should be taken to correct them. |  |  |  |  |  |  |  |  |  | CCM Secretariat | - |
| AGENDA ITEM #6 | CCM activity report for 2021-2022; Introduce the work plan for 2022-2023 1. Approved funding for 2022-2023. 2. The remaining funding has approved for purchase furniture and equipment for the CCM Secretariat office. |  |  |  |  |  |  |  |  |  | CCM Secretariat | - |

To add another 'Agenda Item' highlight the entire row corresponding to the last 'Agenda Item #' in the table. Right click on the mouse and select the ‘Insert’ menu item, then select the ‘Insert Rows Below’ option. Repeat as necessary to add additional rows.

| - NEXT MEETING(includes outstanding agenda items not completed during current meeting) |  |  |
| --- | --- | --- |
| TIME, DATE, VENUE OF NEXT MEETING (dd.mm.yy) |  | N/A |
| PROPOSED AGENDA FOR NEXT MEETING | WRITE THE PROPOSED AGENDA ITEMS IN THE SPACES PROVIDED |  |

To add another 'Agenda Item' highlight the entire row corresponding to the last 'Agenda Item #' in the table. Right click on the mouse and select the ‘Insert’ menu item, then select the ‘Insert Rows Below’ option. Repeat as necessary to add additional rows.

| SUPPORTING DOCUMENTATION | Place an ‘X’ in the appropriate box |  |
| --- | --- | --- |
| ANNEXES ATTACHED TO THE MEETING MINUTES | Yes | No |
| ATTENDANCE LIST | X |  |
| AGENDA | X |  |
| OTHER SUPPORTING DOCUMENTS | X |  |
| APPENDIX 1-10 | X |  |
| IF ‘OTHER’, PLEASE LIST BELOW: |  |  |

| - CHECKLIST (Place‘X’ in the relevant box) |  |  |  |
| --- | --- | --- | --- |
|  | YES | NO |  |
| AGENDA CIRCULATED ON TIME BEFORE MEETING DATE | x |  | The agenda of the meeting was circulated to all CCM members, Alternates and Non-CCM members 2 weeks before the meeting took place. |
| ATTENDANCE SHEET COMPLETED | x |  | An attendance sheet was completed by all CCM members, Alternates, and Non-CCM members present at the meeting. |
| DISTRIBUTION OF MINUTES WITHIN ONE WEEK OF MEETING | x |  | Meeting minutes should be circulated to all CCM members, Alternates and non-members within 1 week of the meeting for their comments, feedback. |
| FEEDBACK INCORPORATED INTO MINUTES, REVISED MINUTES ENDORSED BY CCM MEMBERS* | x |  | Feedback incorporated into revised CCM minutes, minutes electronically endorsed by CCM members, Alternates and non-members who attended the meeting. |
| MINUTES DISTRIBUTED TO CCM MEMBERS, ALTERNATES AND NON-MEMBERS | x |  | Final version of the CCM minutes distributed to CCM members, Alternates and Nonmembers and posted on the CCM’s website where applicable within 15 days of endorsement. |

* Often CCM minutes are approved at the next meeting. For many months can pass before the next scheduled meeting, electronic endorsement of the CCM minutes is considered to be a more efficient method for effective meeting management.

| - glossary for acroynms used in the minutes: |  |
| --- | --- |
| ACROYNM | MEANING |
| MOH | Ministry of Health |
| CCM | Country Coordinating Mechanism |
| NGO | Non-Governmental organization |
| WHO | World Health Organization |
| PCU | Project Coordinating Unit |
| PR | Principal Recipient |
| SR | Sub Recipient |
| SKPA | The Sustainability of HIV Services for Key Populations in Asia (SKPA) Program |
| FBO | Faith-based organisation |
| NCCD | National Center for Communicable Diseases |
| NEMA | National Emergency Management Agency |
| NSC | National Security Council |
| MNUMS | Mongolian National University of Medical Sciences |
| MECS | Ministry of Education, Culture and Science |
| MATC | Mongolian Anti-Tuberculosis Confederation |
| UNFPA | United Nations Population Fund |
| MEF | Mongolian Employer`s Federation |

To add an additional 'Acronym', highlight the entire row corresponding to the last 'Acronym' in the table. Right click on the mouse and select the ‘Insert’ menu item, then select the ‘Insert Rows Below’ option. Repeat as necessary to add additional rows

| - ccm minutes approval: |  |  |  |
| --- | --- | --- | --- |
| APPROVED BY (NAME) > | Kh.Ganbaatar | DATE > | Apr 4, 2022 |
| CCM Chair |  | SIGNATURE > |  |

| - ccm minutes CHECKED by: |  |  |  |
| --- | --- | --- | --- |
| TYPE / PRINT NAME > | B.Oyundari | DATE > | Apr 4, 2022 |
| FUNCTION> | CCM Secretariat coordinator | SIGNATURE > |  |
| - ccm minutes prepared by: |  |  |  |
| TYPE / PRINT NAME > | B.Purevbat | DATE > | Apr 4, 2022 |
| FUNCTION> | CCM Secretariat assistant | SIGNATURE > |  |